Migration to Python3 in Finance

---
Agenda
- Python usage in RRZ
- Software migration and strategies
- Python 3 migration in general
- How we really did it (including graphs)
- Recommendations

---
Python in the RRZ

---
About the RRZ
- IT service provider
- Offers high-availability and secure IT infrastructure
- Roots in banking, active since 1975
- https://www.rrz.co.at/

---
Python Usage
- In use since 2006 for in house tools (initially Jython)
- Business critical applications since 2010
- Application areas
  - Prepare unstructured or obscure data (VSAM, EBCDIC)
  - Cleanup and convert data (e.g. remove characters other applications cannot process)
  - Split and merge data (CSV, XML)
  - Collect data from web sites (e.g. provided by OeNB, EZB)
  - Actual data processing mostly in SQL → more code
- About 3 regular Python commiters (and some occasional ones)
- Since recently also for DevOps

---
Python and external packages
- Python 2.6
- Common packages, mostly to process certain kinds of data: lxml, xlrd, …
- Open sourced own packages:
  - Cutplace – read and validate CSV, PRN etc
  - Loxun – scalable streamed XML writing
- Public domain codec for EBCDIC cp1141

---
Code base to migrate
- About 37 KSLOC (according to pygount, excluding comments and empty lines)
- 20K applications
- 9K tools: build process, converters etc
- 5K common functions used by many applications and tools
- 3K unittests (mostly data driven, e.g. processing prepared CSV files); code coverage about 60%

---
Challenges
- No customer demand → Software runs fine with Python 2.6; at best, Python 3 does not change that
- Development of new features has to continue during migration
- Mainframe centric environment → Python still considered “suspicious”; obscure data formats (e.g. VSAM) and codec (EBCDIC)
- Managed binaries due high security demands → developers can’t just install and run new tools (though virtualenv possible)
- Parallel migration of the core banking system → less COBOL, more PL/1; still Easytrieve and WebFOCUS -_-

---
Software migration
and strategies

---
Software migration
- Goals
  - Keep existing software “alive” without replacing it by new one
  - Ensure low costs for continued maintenance
  - Ensure it can be extended in future with reasonable effort

---
Unified process
for software migration (1/2)
1. Requirements analysis
2. Legacy analysis
3. Target/bridge design
4. Choice of strategy
5. Implementation (transformation)
6. Quality ensurance (testing)
7. Cut-over

---
Software migration strategies
- Reimplementation: rewrite from scratch, keep functionality the same
- Wrapping: preserve internal functions, update only the interfaces so functionality is accessible for more modern systems
- Conversion: modify software so it runs on the new system

---
Cut-over strategies
- Big bang: replace old system in one fell swoop
- Soft: gradually replace old system

---
Areas of software migration
- Programs
- Data
- User interface
- Scheduling

---
References
- E. Ackermann, A. Winter, R. Gimnich (2005). Ein Referenz-Prozess der Software Migration. Softwaretechnik-Trends 25(4), p. 20-22.
- Broadie M. & Stonebreaker L. (1995). Migrating Legacy Systems. San Francisco, Kalifornien: Morgan Kaufmann.
- Sneed H., Wolf, E. & Heilman, H. (2010). Software-Migration in der Praxis: Übertragung alter Softwaresysteme in eine moderne Umgebung. dpunkt Verlag.

---
Python 3 migration in general

---
Basic strategies	(1/2)
- Support only Python 3
  - Fast, easy, clean; use 2to3
  - Limits cut-over strategy to “big bang”
- Version control branches for Python 2 and 3
  - Similar to above but both branches can be maintained in parallel → soft cut-over possible
  - Both branches have to be maintained → additional costs

---
Basic strategies	(2/2)
- Integrate 2to3 in build process
  - One code base, soft cut-over
  - Automatic conversion error prone, might require to implement own hairy transformation rules
- Integrate 3to2 in build process: only on theory
- Single code for both Python 2 and 3
  - One code base, soft cut-over
  - Requires middleware, sometimes “ugly” code

---
References
- Regebro, L. (2013). Porting to Python 3: An in-depth guide. CreateSpace Independent Publishing Platform. http://python3porting.com/
- Ronacher, A. (2013). Porting to Python 3 Redux. http://lucumr.pocoo.org/2013/5/21/porting-to-python-3-redux/
- Schofield, E. (2015). Cheat Sheet: Writing Python 2-3 compatible code. Python Charmers Pty Ltd, Australia. http://python-future.org/compatible_idioms.html

---
How we really did it

---
Milestone 1: EuroPython 2012
- “There this Python 3 thingy”
- Nobody really uses it.
- It doesn’t really work yet.
- There are still major issues and they are messing around with it.

---
Milestone 2: EuroPython 2013
- “Python 3 is gonna come… eventually”
- Things are moving and improving
- People don’t use it but want to use it (kinda)
- Coffee break talk with one of the SQLAlchemy guys about his experience with using one code for Python 2 and 3
- Assessment: many of the packages we need do not work with Python 3 yet

---
Milestone 3: EuroPython 2014
- Attended talk on “Support Python 2 and Python 3 with the same code” by Stefan Schwarzer https://www.youtube.com/watch?v=9vNr_ZzZZAk
- Attended Sprint with Stefan and migrated own open source package loxun
- Experience: make the code work is fairly easy, making the tests work is tedious
- Take away: Single code strategy seems nice

---
Milestone 4: Get started
- After EuroPython 2014
- Created ticket for migration in issue tracker
- Guideline to use “from __future__” imports in new code → Unicode, absolute imports
- Created a list of external packages used by our applications and their state concerning Python 3

---
Milestone 5: cutplace migration
- Open sourced package to read and validate tabular data:
  https://pypi.python.org/pypi/cutplace
- “Javaesque” code (my first “real” Python project)
- Migration as school project
- Allows to try out tools and approaches
- Result: cleaner and faster code that works both with Python 2 and 3
- Critical gap: csv reader and writer → publish csv342: https://pypi.python.org/pypi/csv342/

---
Milestone 6: Migration of core banking starts
- Mid 2014
- Breaks large part of the test suite due new source data models and platform architecture
- Demands most of available resources
- Just what we needed -_-
- Good thing: no real new features planed during banking migration

---
Milestone 7: Summer projects 2015
- Summer intern:
  - makes most of the existing code “from __future__” proof
  - Adds six support for common constructs
  - Migrates optparse to argparse
- Manual tests due test suite by now being mostly useless
- Experience from cutplace migration turns out to be very helpful

---
Milestone 8: infrastructure
- Decision: use Anaconda as Python distribution because it already contains many packages we need and many more that might be useful in future
- Decision: use Pycharm instead of Eclipse+PyDev (better refactoring, svn works out of the box)
- Setup virtual machine with Anaconda+Pycharm
- Order managed binary for Anaconda and Pycharm
- Review current guidelines for Python 2 installations with Ops and mark areas that might change

---
Milestone 9: complete migration
- During Summer 2016
- Result: all the code now works both with Python 2 and 3
- Went pretty smooth
- Again supported by intern
- Throw away code you don’t need any more!

---
Milestone 10: update Ops guidelines
- Workshop with Ops to migrate first server installation to Python 3
- Update guideline documents accordingly
- Also migrates from easyinstall/egg to pip/wheel
- Schedules remained the same, only the path changed

---
Milestone 11: go live
- Each application has its own server (test and production)
- Different schedule per application possible
- Trivial fallback scenario: Python 2 variant is still installed and runnable
- Risk: migration drags on due lack of actual need → eventually just do it

---
Milestone 12: drop Python 2 support
- Cleaner code
- Intern makes it happen

---
Graphical analysis

---
Source code changes
Änderungen am Quellcode
Anzahl der Änderungen

---
Resources
Personeller Aufwand
Aufwand in Personentagen

---
Source code size
Physische Zeilen Quellcode
Anzahl Zeilen

---
Recommendations

---
What went well
- Wait until Python 3, tools and external packages mature
- Use a single code strategy for Python 2 and 3
  → test by comparison, soft cut-over, trivial fallback
- Use middleware: __future__, six, future
- Publish non business critical code that might be of common use as open source→ tests in the wild
- Use interns and school projects → meaningful work for them, fewer resources for company
- Work in the background

---
What to be careful about
- Start working with Ops on deployment concepts (at least weeks before initial migration)
- Unicode; went pretty well for us because the code was already clean due regular encoding issues in externally provided source data
- Difficult migration:
  - csv reading/writing (but much faster now)
  - optparse → argparse
  - Forget urllib, use requests package

---
Areas to look into
- Maybe more tool usage?
- Maybe have a working test suite?
- Pymodernize → seems to have matured considerably

---
Summary
- Migrating to Python 3 went smooth
- Deliberately long duration but few resources
- Key factors: single code, open source, interns